## Summary
AdBrain Control-Plane Gap Assessment
32 enterprise requirements vs the real repo (5-plane audit, 2026-08-30). Honest status; phased.
Status | count
Have / built | 2
Partial | 14
Missing | 14
Not applicable yet | 2
Built this session | 10 sections advanced
Read the 'Gap matrix' tab for the row-by-row detail + evidence.

## Gap matrix
# | Requirement | Current reality (evidence) | Status | Built this session | Phase
1 | Five separate planes (customer/control/data/secrets/observability) | Single customer plane under app/app/*; no control plane exists (no /admin route, no admin API). Data in Supabase; secrets in env+encrypted DB. | Missing | Plane-boundary guard + classification map define the seams | P1
2 | Hard boundary: customer app cannot reach admin ops | No admin plane to breach yet, but no explicit enforced boundary either. | Partial | check-plane-boundary.ts FAILS build if a client file imports the admin/service-role client | Now
3 | Separate control-plane deployment (admin.example.com) | One deployment (rahul-digital). No subdomain/deploy separation. | Missing | - | P2
4 | Zero-trust: verify everything server-side | Per-route getUser() 401 gates + server-side layout guard; JWT via getClaims. But client-provided role/values not all re-verified; RBAC unenforced. | Partial | RBAC catalog gives a server-side can() to verify against | P1
5 | Admin auth stronger than customer (SSO/MFA/keys) | Supabase email+Google only. No MFA/step-up/device mgmt even for customers. | Missing | - | P1
6 | Granular admin RBAC (least privilege) | OrgRole existed (owner/admin/member/viewer) but canEditBrand/canAccessAccount defined and NEVER called. | Partial | rbac.ts: 24-permission catalog + role matrix + can()/requirePermission; platform powers granted to NO tenant role | Now
7 | Four-eyes on high-risk actions | None. | Missing | audit_log has an approval jsonb column ready for it | P1
8 | Immutable audit log | None. Only decision_triples (mutable, UPDATEd in place); no actor/action/before-after/request-id. | Missing | 0015 audit_log: append-only, DB trigger blocks UPDATE/DELETE, RLS-deny, secret-scrubbed. Wired to credential.store + judgment.label | Now
9 | DB-level authz + proven tenant isolation | RLS deny-by-default on ~27 tables but only 7 policies; isolation enforced by ~94 manual .eq filters; NO cross-tenant test. | Partial | Plane guard added; a seeded cross-tenant DB test is the next step | P1
10 | Service-to-service auth (no implicit trust) | Only cron shared-secret, and it uses a non-timing-safe compare (callback route). | Missing | - | P1
11 | Secret management (never in client/code/logs) | STRONG: all keys server-only env; OAuth tokens AES-256-GCM encrypted (lib/crypto.ts); /health exposes presence only; no client leaks. | Have | check-plane-boundary guards NEXT_PUBLIC secret-shaped names + client admin imports | Now
12 | Secret rotation / revocation / last-used | Thin: expires_at + account status only. No rotation, revoke endpoint, last-used, or key versioning. | Partial | credential.rotate/revoke actions defined in the audit catalog | P1
13 | AI data security (tenant boundaries in pipeline) | Agents are read-only; but AI calls carry no user/org/purpose/classification; recordAiCall is a global anonymous counter. | Partial | Classification tiers + audit spine enable per-call attribution | P1
14 | Data classification (5 tiers) | None. | Missing | classification.ts: every table -> PUBLIC/INTERNAL/CONFIDENTIAL/SENSITIVE/HIGHLY_SENSITIVE -> encryption/logging/access/retention | Now
15 | AI prompt security (separate instruction layers) | User input string-concatenated into one user-role message across all providers; only a numeric-grounding recheck. | Missing | Documented; structured system/user/data layering is the next AI-layer build | P1
16 | Agent tool permissions (least privilege) | Agents are toolless single LLM calls - cannot act on the account. Least-privilege by absence. | Partial | Acceptable now; formal per-agent tool scoping when agents gain tools | P2
17 | Production write protection (read/write/dangerous) | Creative is draft-only; no dangerous-write class or extra controls. | Partial | Kill switches add an instant brake on dangerous subsystems | Now
18 | Credit ledger security | No credits system, no ledger, no balance column. | N/A | audit_log + a ledger pattern ready when billing is built | P1
19 | Payment security (provider-authoritative, webhook idempotency) | No payment provider, no webhooks, no card data. | N/A | - | P1
20 | Controlled data export | None. | Missing | data.export permission + audit action defined | P1
21 | Deliberate account deletion | Cascade FKs exist; no deliberate soft/hard-delete + revoke-sessions flow. | Partial | account.delete audit action defined | P1
22 | Incident response system | None. | Missing | - | P2
23 | Break-glass emergency access | None. | Missing | - | P2
24 | Security alerts (failures/exports/escalation) | Only an AI-budget alert (alerts, does not brake). | Partial | Kill switches turn the alert into an actual brake | P1
25 | Security notifications on critical events | Notification Center exists but not wired to security events. | Partial | audit_log is the event source to wire notifications to | P1
26 | Backend change control (versioned config, rollback) | Thresholds hardcoded in TS; 'change value and forget'. | Missing | audit_log before/after + system_flags give a versioned start | P1
27 | Prompt/rule/formula governance (draft->publish, immutable versions) | Hardcoded TS + a 1,061-row JSON; no lifecycle; 991 'planned' rules were served as in-force; no version pin on decisions. | Missing | FIXED: applicableRules now serves only in-force (shipped/partly) rules; full lifecycle+version-pin is next | P1
28 | Security testing suite | Many check:* scripts but no auth/authz/injection/SSRF/tenant suite. | Partial | Added 5 security checks (audit, flags, rbac, plane, classification) = 121 assertions into check:all | Now
29 | Red-team (attacker with a customer account) | Never run. | Missing | - | P1
30 | Every subsystem: owner/boundary/audit/rollback | Improving; security subsystems now have clear boundaries + checks. | Partial | This foundation adds boundary+audit+tests for 5 security subsystems | Now
31 | No assumptions - ground in real docs/code | - | Have | This whole assessment is grounded in a 5-agent repo audit, not assumptions | Now
32 | Final enterprise quality gate (33-point checklist) | Most items open until P1/P2. | Partial | 6 of 33 gate items now green (secrets, audit, kill switch, classification, RBAC model, plane boundary) | Ongoing